## Start Here
MERIDIAN | 90-Day AI Security Starter
Reference Lines for AI Security
What this is | The 17-control starting baseline from MERIDIAN, the free AI security control catalog at meridian.htora.dev. These are the controls a team that USES AI (buys tools with AI inside, or lets staff use AI services) can stand up in about 90 days. It is the same M-1 + Use baseline the site produces from its one-tap preset and its 6-question readiness assessment.
Who it is for | Organizations that consume AI rather than train or host their own models. If you build or host models, this baseline is your floor, not your ceiling. The full catalog has 65 controls across three maturity tiers.
How to use it | 1. Open the 90-Day Tracker tab. 2. Assign an owner and target date to each of the 17 controls. 3. Set Status as you go (Not started / In progress / Done / N/A). 4. Watch the Progress tab update automatically. Each control carries a plain statement and the assessor evidence that proves it is real, not just written down.
The crosswalk | Every control maps to the frameworks you already answer to. The Crosswalk Reference tab shows which of the 14 frameworks each control satisfies, so one piece of work counts in many places: SAIF, ATLAS, NIST AI RMF, OWASP LLM and Agentic, AICM, AISMM, ISO 42001, 800-53, EU AI Act, GDPR, AISVS, and Databricks DASF.
Full catalog | Catalog, whitepaper, OSCAL export, and the readiness assessment are free at meridian.htora.dev. This workbook is a starting point, not the whole thing.
Baseline | 17 controls · ~90 days · tier M-1 · applicability = Use
Version | MERIDIAN v1.6 · 65 controls · 429 verified crosswalk mappings · 14 frameworks
License | CC BY 4.0 · © 2026 Habib Tora · meridian.htora.dev

## 90-Day Tracker
90-Day Tracker · 17-control AI security starter baseline
# | ID | Control | Function | Status | Owner | Target date | Statement (what "done" means) | Assessor evidence | Notes
1 | GV-01 | AI Security Policy | Govern | Not started |  |  | The organization maintains an approved AI security policy covering development, acquisition, and use of AI systems. | An approved, dated AI security policy exists, covers build, acquire, and use scope, and shows review within the last 12 months.
2 | DS-01 | AI System Inventory | Discover | Not started |  |  | All AI systems (built, acquired, embedded, SaaS) are inventoried with owner, purpose, and impact tier. | The AI inventory lists sampled known systems with owner, purpose, and impact tier, and spot checks find no unlisted production AI.
3 | DT-01 | AI Interaction Logging Standard | Detect | Not started |  |  | Prompts, outputs, tool calls, retrievals, and model versions are logged to the SIEM per a defined standard. | The SIEM contains prompts, outputs, tool calls, retrievals, and model versions for sampled AI systems, conforming to the logging standard.
4 | RS-01 | AI Incident Response Playbooks | Respond | Not started |  |  | IR playbooks cover AI-specific scenarios: injection compromise, poisoning, model theft, harmful-output events. | AI-specific playbooks exist for injection compromise, poisoning, model theft, and harmful-output scenarios, with exercise records within 12 months.
5 | GV-02 | Named AI Risk Ownership | Govern | Not started |  |  | A named senior role is accountable for AI security risk, with documented decision authority. | An org chart or charter names the accountable AI risk role, and meeting minutes or risk decisions demonstrate that authority being exercised.
6 | SC-02 | Sensitive Data Minimization | Secure | Not started |  |  | PII and regulated data is minimized, masked, or excluded from training and retrieval corpora. | Sampled corpora show masking or exclusion of regulated data, and scan or DLP reports confirm minimization.
7 | GV-03 | AI Acceptable Use Policy | Govern | Not started |  |  | An AUP defines permitted and prohibited AI uses, including data that may not be submitted to AI systems. | A published AUP enumerates permitted and prohibited AI uses and prohibited data classes, with distribution or attestation records for the workforce.
8 | GV-04 | AI Risk Assessment Process | Govern | Not started |  |  | AI systems undergo documented security risk assessment before deployment and on material change. | Completed risk assessment artifacts exist for sampled AI systems, dated before deployment and re-run after material changes.
9 | DS-05 | Data Classification for AI Use | Discover | Not started |  |  | Data is classified for AI eligibility (trainable, retrievable, prohibited) before ingestion. | Classification labels (trainable, retrievable, prohibited) exist on sampled datasets with dates preceding their ingestion records.
10 | SC-05 | Model Access Control | Secure | Not started |  |  | Model endpoints require authenticated, least-privilege, auditable access. | Endpoint configurations require authentication, and access reviews plus audit logs exist for sampled model endpoints.
11 | GV-07 | Vendor AI Risk Assessment | Govern | Not started |  |  | Third-party AI services and embedded-AI products are risk-assessed before procurement. | Vendor AI risk assessments exist for sampled procurements and are dated before contract signature.
12 | GV-10 | AI Security Awareness & Training | Govern | Not started |  |  | Role-based training covers AI threats (prompt injection, data leakage, shadow AI) for builders, defenders, and users. | Training records show role-based AI security training completion for builders, defenders, and users within the defined cycle.
13 | SC-11 | Prompt Injection Defense | Secure | Not started |  |  | Layered defenses (input filtering, instruction hierarchy, context isolation) mitigate direct and indirect prompt injection. | Layered injection defenses are documented, and adversarial test results demonstrate mitigation of direct and indirect injection for sampled systems.
14 | SC-12 | Input Validation & Filtering | Secure | Not started |  |  | Untrusted inputs (user, retrieved, inter-agent) are validated and sanitized before reaching the model. | Input validation rules exist in code or configuration, and test cases show sanitization across user, retrieved, and inter-agent input paths.
15 | SC-13 | System Prompt Protection | Secure | Not started |  |  | System prompts contain no secrets and are protected against disclosure; disclosure is treated as expected, not catastrophic. | System prompts pass secret scans, and disclosure test results show no privilege or data-access change from prompt exposure.
16 | SC-14 | Output Handling & Encoding | Secure | Not started |  |  | Model outputs are treated as untrusted: encoded, validated, and never executed or rendered directly. | Code review or configuration shows output encoding and validation, and no sampled flow executes or renders model output directly.
17 | SC-17 | Secrets Hygiene in AI Pipelines | Secure | Not started |  |  | Credentials are never embedded in prompts, training data, or model artifacts; pipeline secrets are vaulted. | Secret scans of prompts, datasets, and model artifacts return clean, and pipeline secrets resolve from a vault in sampled configurations.

## Crosswalk Reference
Crosswalk Reference · what each baseline control satisfies
ID | Control | # frameworks | # mappings | Frameworks satisfied
GV-01 | AI Security Policy | 3 | 3 | ISO/IEC 42001 · NIST SP 800-53 · NIST AI Risk Management Framework
DS-01 | AI System Inventory | 6 | 6 | Databricks AI Security Framework · EU AI Act · NIST SP 800-53 · NIST AI 600-1 · NIST AI Risk Management Framework · OMB Memoranda
DT-01 | AI Interaction Logging Standard | 8 | 10 | CSA AI Controls Matrix · Databricks AI Security Framework · EU AI Act · GDPR · NIST SP 800-53 · NIST AI 600-1 · OWASP AI Security Verification Standard · SANS AI Security Maturity Model
RS-01 | AI Incident Response Playbooks | 4 | 4 | NIST SP 800-53 · NIST AI Risk Management Framework · OWASP AI Security Verification Standard · SANS AI Security Maturity Model
GV-02 | Named AI Risk Ownership | 4 | 4 | EU AI Act · ISO/IEC 42001 · NIST SP 800-53 · NIST AI Risk Management Framework
SC-02 | Sensitive Data Minimization | 7 | 9 | Databricks AI Security Framework · GDPR · ISO/IEC 42001 · NIST SP 800-53 · NIST AI 600-1 · OWASP AI Security Verification Standard · OWASP Top 10 for LLM Applications
GV-03 | AI Acceptable Use Policy | 3 | 3 | CSA AI Controls Matrix · NIST SP 800-53 · NIST AI Risk Management Framework
GV-04 | AI Risk Assessment Process | 6 | 6 | EU AI Act · GDPR · ISO/IEC 42001 · NIST SP 800-53 · NIST AI 600-1 · NIST AI Risk Management Framework
DS-05 | Data Classification for AI Use | 8 | 8 | CSA AI Controls Matrix · Databricks AI Security Framework · EU AI Act · GDPR · NIST SP 800-53 · NIST AI 600-1 · OWASP AI Security Verification Standard · OWASP Top 10 for LLM Applications
SC-05 | Model Access Control | 4 | 7 | CSA AI Controls Matrix · Databricks AI Security Framework · NIST SP 800-53 · OWASP AI Security Verification Standard
GV-07 | Vendor AI Risk Assessment | 5 | 5 | CSA AI Controls Matrix · NIST SP 800-53 · NIST AI 600-1 · NIST AI Risk Management Framework · OWASP AI Security Verification Standard
GV-10 | AI Security Awareness & Training | 7 | 8 | Databricks AI Security Framework · EU AI Act · ISO/IEC 42001 · NIST SP 800-53 · NIST AI 600-1 · OWASP Top 10 for Agentic Applications · SANS AI Security Maturity Model
SC-11 | Prompt Injection Defense | 8 | 8 | MITRE ATLAS · Databricks AI Security Framework · EU AI Act · NIST AI 600-1 · OWASP AI Security Verification Standard · OWASP Top 10 for Agentic Applications · OWASP Top 10 for LLM Applications · Google Secure AI Framework
SC-12 | Input Validation & Filtering | 6 | 9 | MITRE ATLAS · Databricks AI Security Framework · NIST SP 800-53 · OWASP AI Security Verification Standard · OWASP Top 10 for Agentic Applications · OWASP Top 10 for LLM Applications
SC-13 | System Prompt Protection | 4 | 6 | MITRE ATLAS · Databricks AI Security Framework · OWASP AI Security Verification Standard · OWASP Top 10 for LLM Applications
SC-14 | Output Handling & Encoding | 4 | 7 | Databricks AI Security Framework · NIST SP 800-53 · OWASP AI Security Verification Standard · OWASP Top 10 for LLM Applications
SC-17 | Secrets Hygiene in AI Pipelines | 5 | 6 | MITRE ATLAS · Databricks AI Security Framework · NIST SP 800-53 · OWASP AI Security Verification Standard · OWASP Top 10 for LLM Applications

## Progress
Progress | live from the 90-Day Tracker tab
Overall
Controls total | 17
Done | 0
In progress | 0
Not started | 17
N/A | 0
Completion | 0%
By function
Function | Total | Done
Govern | 6 | 0
Discover | 2 | 0
Secure | 7 | 0
Detect | 1 | 0
Respond | 1 | 0
Assure | 0 | 0